## Sheet1
DTIT Own Apllication
Application Name | Frontend Design | Backend Raw Code | Api/Postman | Status | Server Status | `
Word to Pdf |  | Completed | Completed | Finished |  | done
Pdf to Word |  | Completed | Completed | Finished |  | done
Pdf to excel |  | Completed | Completed | Finished |  | done
PDf Crop |  | Frontend Work |  |  |  | FE
Pdf to PowerPoint |  | Completed | Not Completed | Pending |  | needsome work
Excel to pdf |  | Completed | Not Completed | Pending |  | done
PowerPoint to pdf |  | Process Going on | Not Completed | Pending |  | done
Jpg to pdf |  | Almost Completed | Not Completed | Pending |  | done
Pdf to jpg |  | Completed | Completed | Finished |  | done
Add page no |  | Completed | Completed | Finished |  | done
Merge Pdf |  | Process Going on | Not Completed | Pending
Split Pdf |  | Process Going on | Not Completed | Pending
Compress Pdf |  | Process Going on | Not Completed | Pending
Pdf to Powepoint |  | Not Yet Started | Not Completed | Pending
Speech to Text and Text to Speech |  | Completed | Completed | Finished
Voice Cloning |  | Completed | Completed | Finished
Resume Template |  | Completed | Completed | Finished
Add Background Colour white |  | Completed | Not Completed | Pending
pdf Rotate |  | Frontend Work |  |  |  | FE
Image Enhancer |  | Process Going on | Not Completed | Pending
Bg Remover |  | Completed | Not Completed | Pending
Sign Pdf |  | Process Going on | Not Completed | Pending
Rotate Pdf |  | Frontend Work |  |  |  | FE
Edit Pdf |  | Process Going on | Not Completed | Pending
Text Extraction |  | Completed | Completed | Finished
Pencil Art |  | Completed | Not Completed | Pending
FaceSwap |  | Completed | Not Completed | Pending
DTIT Own LLM (LIKE CHATGPT) |  | Process Going on | Not Completed | Pending
English Learning LLM |  | Process Going on | Not Completed | Pending
Translate Audio |  | Process Going on | Not Completed | Pending